## Version Control
CoUPon: Check Out UP Orgs Now!
Requirements Traceability Matrix

Submitted to:	Ma. Rowena C. Solamo
	Faculty Member
	Department of Computer Science
	College of Engineering
	University of the Philippines, Diliman

Submitted by:	Araya, Carl
	Comia, Camille
	Florita, Nikki

In partial fulfillment of Academic Requirements
for the course
CS 191 Software Engineering
1st Sem AY <2017-2018>

History Revision:

Revision Date	Person Responsible	Version Number	Modification
10/16/17	Nikki Florita	1.0	Initial Draft
10/17/17	Nikki Florita	1.1	Continuation of initial draft
10/25/17	Nikki Florita	1.2	Added verification for student form and log in for organizations

## Requirements
RTM ID	Use Case No.	Description	Scenario No	Scenario Description	Priority Status	Has Prototype?
UC-1.0-S1	Use Case 1.0	Provide organization description: the student organization will give the moderators information to be posted on the website	S1	Organization provides the content	Must Have	no
UC-1.0-S2			S2	Optional data is given	Should Have	no
UC-1.0-S3			S3	Data given is incomplete	Must Have	no
UC-2.0-S1	Use Case 2.0	Maintain website: the moderators make changes to the website	S1	Organization give new data to the moderators to add to the website	Must Have	no
UC-2.0-S2			S2	Information given by organization has problems	Must Have	no
UC-2.1-S1	Use Case 2.1	Add organization profile: creation of a new profile for a newly-joined organization	S1	Moderator adds the organization profile	Must Have	no
UC-2.2-S1	Use Case 2.2	Modify organization profile: modify the content of a profile as requested by the organization	S1	Moderator modifies the organization profile	Must Have	no
UC-2.2-S2			S2	Moderator modifies profile that does not exist	Should Have	no
UC-2.3-S1	Use Case 2.3	Delete organization profile: a student organization’s profile in the system is deleted as requested by the organization	S1	Moderator deletes org profile	Must Have	no
UC-3.0-S1	Use Case 3.0	View org profile: student visits the website	S1	A student view the website	Must Have	no
UC-3.0-S2			S2	Student notices a bug in the website	Should Have	no
UC-4.0-S1	Use Case 4.0	Provide application form: moderator provides application form for student visitors to fill out	S1	No database exists yet	Must Have	no
UC-4.0-S2			S2	Previous database already exists	Must Have	no
UC-5.0-S1	Use Case 5.0	Fill out application form: student visitor fills out the application form	S1	Submit form	Must Have	no
UC-5.0-S2			S2	Cancel form	Should Have	no
UC-5.0-S3			S3	Send verification via email	Must Have	no
UC-5.0-S4			S4	Email is verified	Must Have	no
UC-5.0-S5			S5	Email is not verified	Must Have	no
UC-6.0-S1	Use Case 6.0	View student’s personal information: organization views the data of students who fill out the application form for their organization	S1	View data	Must Have	no
UC-6.0-S2			S2	Log In: username and password accepted	Must Have	no
UC-6.0-S3			S3	Log In: username is incorrect	Must Have	no
UC-6.0-S4			S4	Log In: password is incorrent	Must Have	no
UC-6.0-S5			S5	Log In: username and password both incorrect	Must Have	no
UC-6.0-S6			S6	Log Out	Must Have	no
UC-6.0-S7			S7	Specific student information only appears on organization accounts he would like to join	Must Have	no

## Must Have
RTM ID	Use Case No.	Description	Scenario No	Scenario Description	Story Points(1-55)	Value Points	Bang for the Buck	Legend
UC-6.0-S6			S6	Log Out	1	8	8		Use Case 2
UC-6.0-S2			S2	Log In: username and password accepted	2	8	4		Use Case 3
UC-6.0-S3			S3	Log In: username is incorrect	2	8	4		Use Case 4
UC-6.0-S4			S4	Log In: password is incorrect	2	8	4		Use Case 5
UC-6.0-S5			S5	Log In: username and password both incorrect	2	8	4		Use Case 6
UC-5.0-S4			S4	Email is verified	5	13	2.6
UC-5.0-S5			S5	Email is not verified	5	13	2.6		Sprint 1
UC-3.0-S1	Use Case 3.0	View org profile: student visits the website	S1	A student view the website	34	55	1.6176470588		Sprint 2
UC-5.0-S1	Use Case 5.0	Fill out application form: student visitor fills out the application form	S1	Submit form	34	55	1.6176470588		Sprint 3
UC-2.3-S1	Use Case 2.3	Delete organization profile: a student organization’s profile in the system is deleted as requested by the organization	S1	Moderator deletes org profile	21	21	1		Sprint 4
UC-6.0-S1	Use Case 6.0	View student’s personal information: organization views the data of students who fill out the application form for their organization	S1	View data	55	34	0.6181818182		Sprint 5
UC-2.1-S1	Use Case 2.1	Add organization profile: creation of a new profile for a newly-joined organization	S1	Moderator adds the organization profile	34	21	0.6176470588
UC-4.0-S1	Use Case 4.0	Provide application form: moderator provides application form for student visitors to fill out	S1	No database exists yet	13	5	0.3846153846
UC-4.0-S2			S2	Previous database already exists	13	5	0.3846153846
UC-2.2-S1	Use Case 2.2	Modify organization profile: modify the content of a profile as requested by the organization	S1	Moderator modifies the organization profile	55	21	0.3818181818
UC-5.0-S3			S3	Send verification via email	55	13	0.2363636364